## Sheet1
Admin Side
No. | Page | Status | Hrs |  | Date | Comments
1 | CMS Users | Completed
2 | Banners | Completed
3 | Departments | Started
4 | AboutUs
5 | Clients
6 | Online Consultation
7 | Pharmacy
8 | Surgical Procedures
9 | Special Offers
10 | Events
11 | Media
12 | Media Category
13 | Testimonials |  |  |  |  | Can't find the section in english home page. Only in arabic
Site Side
No. | Page | Status | Hrs |  | Date | Comments
1 | Site Side intial setup |  | 4
2 | Home |  | 4
3 | About |  | 2 |  |  | Our Values not need to be dynamic right?
4 | Online Consultation |  | 2
5 | Departments |  | 2
6 | Department Details (With doctor listing and link to book to appointment) |  | 3
7 | Pharmacy |  | 1.5
8 | Special Offers |  | 1.5
9 | Contact Us |  | 4
10 | Find Your Doctor |  | 3
11 | Events |  | 2
12 | Event Details |  | 2.5
13 | Surgical Procedures |  | 2
14 | Surgical Procedures Details |  | 2
15 | Media |  | 2.5
16 | Site Side Arabic |  | 28
Book Appointment
No. | Task | Status | Hrs | Status | Date | Comments
1 | Initial SetUp of API Fetching(request, response and exception handling) |  | 25
2 | Logger Setup |  | 8
3 | SMS Gateway setup |  | 8
4 | Login(with sms verification) |  | 10
5 | SignUp |  | 3
6 | Forget Password |  |  |  |  | Do we need password? Is sms verification enough?
7 | Get All Departments |  | 1
8 | Doctor Listing With Department Filter |  | 4 |  |  | Doctor profile page not available(There is a profile button in listing)
9 | Search Doctor, Speciality |  | 2
10 | Profile (View and Edit) |  | 1.5 |  |  | Edit profile API is not currently available
11 | LogOut |  | 0.5
12 | Appointments(All, Upcoming, Recent, Cancelled) |  | 4 |  |  | 1. Currently upcoming appointment and history is separate end points(Created based on the earlier design). May be we need to merge it together 2. Appointments within how many days "Recent" need to show
13 | Appointment Details with Cancel Appointment |  | 3
14 | Book Appointment(Fetch available slots, book consultation) |  | 12 |  |  | Need to find appropriate jQuery calender control. If designer can set the proper calender control in page that will be helpful
15 | Reports |  | 2
16 | Report Details |  |  |  |  | API Pending
17 | Earn Loyalty |  |  |  |  | API Pending
18 | My Rewards |  |  |  |  | API Pending

## Queries
about us --> separate fields for description mission and vision?
Events, surgical procedures and media lonks are only there in footer