## Sheet1
Book Appointment
No. | Task | Status | Hours | Expected Completion Date | Date | Comments
1 | Logger Setup and Exception Handling | Completed | 8 | 2021-05-25
2 | Get All Departments | Completed | 3
3 | Doctor Listing and Department Filter | Completed | 6 |  |  | Doctor profile page not available(There is a profile button in listing)
4 | Search Doctor, Speciality | Completed | 3 | 2021-05-25
5 | Profile (View and Edit) | Edit Pending |  |  |  | Edit profile API is not currently available
6 | Appointments(All, Upcoming, Recent, Cancelled) | Completed | 8 | 2021-05-25 |  | 1. Currently upcoming appointment and history is separate end points(Created based on the earlier design). May be we need to merge it together
7 | Appointment Details with Cancel Appointment | Completed | 3 | 2021-06-01 |  | After cancellation, do we need to show anything like appintment success? Currently just showing cancellation successful
8 | Book Appointment a) Fetch available slots of doctor based on the date selected. b) patient details design integration c) Reschedule slot d) Save the appointment | Completed | 20 | 2021-06-01 |  | 1. Booking for name is not updated in all cases. 2. If a appointment is cancelled, the timeslot is not displaying for the doctor for that date (get slot api issue).
9 | Reports (Listing) | Completed | 2 | 2021-06-01
10 | Report Details |  |  |  |  | API Pending
11 | Earn Loyalty |  |  |  |  | API Pending
12 | My Rewards |  |  |  |  | API Pending
Comments from Ramshad and Farhan
2 | Registration function to be done | Completed | 3
3 | Sign in/sign up needs otp function | Completed
4 | Provide arrow marks for categories swipe left |  |  |  |  | Designer
5 | Remove recent button from my appointments page | Completed | 0
6 | Add canceled label in red colur | Completed | 0
10 | check view my apointmnet button colour
12 | logout option & my rewards option needs to be functional
| Need to keep qatar code in phone number field | Completed | 1
| Need to keep login & sign Up deisgn & flow same as HTML | Completed | 8
| remove forget password option | Completed
| Add static design for the earn-rewards and loyalty pages | Completed | 2.5
| Show confirmation before cancellation of appointment | Completed | 1
| Integrated newly designed page after cancellation of an appointment | Completed | 1
| Ooreedo Integration | Completed | 10
| Upon sign up it needs to land in homepage, currently it is taking to login page inorder to login again and verify with otp | Completed | 0.5
| Need to remove nationality function, as it is of no use | Completed
| Upon typing wrong otp it should show error on pop up, as of now showing in login page | Completed | 1
| OTP Resend option with 30 second timer in login and signup | Completed | 3
find a doctor button to be linked with home button
need to link the EMC website URL - on visit website button
need to provide small cursor/arrow for department categories
| check for nationallity, passport number options from API |  |  |  |  | API needed to integrate this
Need to option for Arabic translation
Provide admin panel HTML to aneesh
| Provide common avatar deisgn to aneesh |  |  |  |  | Image is not given
In admin we need option to manage the application banners and departments icon
| Meeting |  | 2
|  | Hours | 86

## Queries
about us --> separate fields for description mission and vision?
Events, surgical procedures and media lonks are only there in footer