## Sheet1
Admin Side
No. | Page | Status | Hrs |  | Date | Comments
1 | CMS Users | Completed
2 | Banners | Completed
3 | Departments | Started
4 | AboutUs
5 | Clients
6 | Online Consultation
7 | Pharmacy
8 | Surgical Procedures
9 | Special Offers
10 | Events
11 | Media
12 | Media Category
13 | Testimonials |  |  |  |  | Can't find the section in english home page. Only in arabic
Site Side
No. | Page | Status | Hrs |  | Date | Comments
1 | Site Side intial setup |  | 4
2 | Home |  | 4
3 | About |  | 2 |  |  | Our Values not need to be dynamic right?
4 | Online Consultation |  | 2
5 | Departments |  | 2
6 | Department Details (With doctor listing and link to book to appointment) |  | 3
7 | Pharmacy |  | 1.5
8 | Special Offers |  | 1.5
9 | Contact Us |  | 4
10 | Find Your Doctor |  | 3
11 | Events |  | 2
12 | Event Details |  | 2.5
13 | Surgical Procedures |  | 2
14 | Surgical Procedures Details |  | 2
15 | Media |  | 2.5
16 | Site Side Arabic |  | 28
Book Appointment
No. | Task | Status | Hrs | Status | Date | Comments
2 | Logger Setup and Exception Handling | In Progress | 8 | 2021-05-25
7 | Get All Departments | Completed | 3
8 | Doctor Listing and Department Filter | Completed | 6 |  |  | Doctor profile page not available(There is a profile button in listing)
9 | Search Doctor, Speciality | Pending | 3 | 2021-05-25
10 | Profile (View and Edit) | Edit Pending |  |  |  | Edit profile API is not currently available
12 | Appointments(All, Upcoming, Recent, Cancelled) | Pending | 6 | 2021-05-25 |  | 1. Currently upcoming appointment and history is separate end points(Created based on the earlier design). May be we need to merge it together
13 | Appointment Details with Cancel Appointment | Pending | 3 | 2021-06-01
14 | Book Appointment a) Fetch available slots based on the date selected, book consultation) b) Reschedule slot c) Save the appointment | Pending | 20 | 2021-06-01
15 | Reports (Listing) | Pending | 2 | 2021-06-01
16 | Report Details |  |  |  |  | API Pending
17 | Earn Loyalty |  |  |  |  | API Pending
18 | My Rewards |  |  |  |  | API Pending

## Queries
about us --> separate fields for description mission and vision?
Events, surgical procedures and media lonks are only there in footer